## CRUD
NR - Full Stack Web Development Project - Lumina, A Skin Care E-commerce Store - Features & CRUD Process Mapping
Roles | No | Process | CRUD | Sub Process | Description
User | 1 | User Registration & Profiling | C | User Registration | Implement a registration form for users to create accounts. Collect necessary information (e.g., username, email, password).
|  |  | R | View Profile | Users can view their own profiles, including order history and personal information.
|  |  | U | Update Profile | Users should be able to edit their profile information (e.g., change password, update shipping address).
|  |  | D | Delete Account | Users can request and do account deletion.
| 2 | Product Listing & Search | R | Product Listings | Display a list of available skincare products. Users can view product details, including images, descriptions, and prices.
|  |  | R | Product Search | Enable users to search for specific products based on keywords or filters (e.g., category, price range).
| 3 | Shopping Cart | C | Add to Cart | Allows users to select a product and add it to their shopping cart. Typically involves specifying the product, quantity, and any relevant options (e.g., size, color).
|  |  | R | View Cart | Displays the contents of the user’s shopping cart. Shows a summary of selected products, quantities, prices, and the total cost.
|  |  | U | Edit Cart | Adjust products and quantity
|  |  | D | Delete Products in Cart | Allows users to remove specific products from their cart. Useful when users change their minds or want to remove unwanted items.
| 4 | Check Out & Ordering | C | Check Out & Make Order | Allows users to finalize their purchase by reviewing their selected items, providing shipping and payment details, and confirming the order.Initiates the process of creating an order in the system.
|  |  | R | View Order | Displays details of a previously placed order, including product names, quantities, prices, shipping information, and order status. Helps users track their purchases and verify order accuracy.
|  |  | D | Cancel an Order | Enables users to cancel an existing order before it is shipped or delivered. Typically involves updating the order status and potentially refunding the payment.
| 5 | Product Rating & Reviewing | C | Create Reviews | Allows users to submit their feedback and ratings for a specific product. Users can write comments and assign a rating (e.g., stars) based on their experience.
|  |  | R | View Reviews | Displays aggregated reviews and ratings for a product. Helps potential buyers make informed decisions by showing the collective opinions of other users.
|  |  | U | Update Reviews | Enables users to modify their previously submitted reviews. Users can edit their comments or change their ratings if their opinion changes over time.
|  |  | D | Delete Reviews | Allows users to remove their own reviews from a product. Useful if a user wants to retract or update their feedback.
Admin | 1 | Product Listing & Edit | C | Product Creation | Admins can add new skincare products to the website. This involves specifying details such as product name, description, price, images, and category.
|  |  | R | Product List Viewing | Admins can see the list of existing skincare products listed in the website and their details.
|  |  | U | Product Editing | Admins can modify product details (e.g., update prices, change descriptions, upload new images).
|  |  | D | Product Deletion | Admins can delete products listing.
| 2 | Order Processing | R | See Customer Order | Allows the admin to view details of a specific customer’s order. Provides information such as ordered products, quantities, shipping address, and payment status.
|  |  | U | Update Order Status | Enables the admin to modify the status of an order (e.g., pending, shipped, delivered). Helps track the progress of orders and communicate updates to customers.

## Pages
No | Title | Description | Content
1 | Home
2 | All Product
Category Page
Search Result
2 | Detail Product
3 | My Account
4 | Registration
5 | Login
6 | Cart
7 | Check Out
8 | Payment
9 | Confirm Payment
10 | Order
11 | Order Status
12 | Admin Page
13 | Product Detail Edit
14 | All Product Listing
15 | Customer Orders
16 | Order Detail
17 | About Us
18 | Contact Us
19 | Terms & Conditions
20 | Privacy Policy

## Timeline
2024-06-01
No | Aspect | Agenda | Due Date | Days Left
1 | Front End | Home Page | Done
2 | Front End | Login / Register Page | Done
3 | Front End | Product Detail Page | 2024-05-15 | -17
4 | Front End | Admin Page (Change Banner, Product List (Add, Delete), Order List, Change Password) | 2024-05-17 | -15
5 | Front End | Customer Page (My Cart, My Orders) | 2024-05-17 | -15
6 | Back End | Login and Register Process | 2024-05-19 | -13
7 | Back End | Change Password Process | 2024-05-19 | -13
8 | Back End | Product List Process | 2024-05-24 | -8
9 | Back End | Check Out Process | 2024-05-27 | -5
12 | All | Gold Challenge Submission Due Date | 2024-06-02 | 1
Formulas:
Due Date = [Due Date, row above]+2
Due Date = [Due Date, row above]

## Data
No | Brand | Product name | Price | Image link
1 | SKINTIFIC | MSH Niacinamide Brightening Moisture Gel | 121000 | product-image-1.png
2 | SKINTIFIC | 5X Ceramide Barrier Moisture Gel | 135000 | product-image-2.jpg
3 | SKINTIFIC | Cover All Perfect Cushion | 180000 | product-image-3.png
4 | SKINTIFIC | 5X Ceramide Serum Sunscreen | 52000 | product-image-4.png
5 | SKINTIFIC | Alaska Volcano Pore Clay Stick | 86000 | product-image-5.png
6 | SKINTIFIC | REFILL Cover All Perfect Cushion | 133000 | product-image-6.png
7 | SKINTIFIC | Mugwort Acne Clay Stick | 87000 | product-image-7.png
8 | SKINTIFIC | Truffle Biome Skin Reborn Cream Gel Moisturizer | 148000 | product-image-8.png
9 | SKINTIFIC | Niacinamide Brightening Essence Toner | 40000 | product-image-9.png
10 | SKINTIFIC | Brightening Booster Set | 321000 | product-image-10.png
11 | SKINTIFIC | All Day Light Sunscreen Mist SPF 50 PA++++ | 74000 | product-image-11.png
12 | SKINTIFIC | 5% Panthenol Acne Calming Water Gel | 130000 | product-image-12.png
13 | SKINTIFIC | 5X Ceramide Soothing Toner | 34000 | product-image-13.png
14 | SKINTIFIC | Glycolic Acid Daily Clarifying Toner | 115000 | product-image-14.png
15 | SKINTIFIC | Cushion Set | 290000 | product-image-15.png
16 | SKINTIFIC | 5X Ceramide Barrier Repair Moisturizer Gel | 39000 | product-image-16.png
17 | SKINTIFIC | 10% Vitamin C Brightening Glow Serum | 143000 | product-image-17.png
18 | SKINTIFIC | Aqua Light Daily Sunscreen SPF 35 PA +++ | 88000 | product-image-18.png
19 | SKINTIFIC | Symwhite 377 Dark Spot Moisture Gel | 138000 | product-image-19.png
20 | SKINTIFIC | SymWhite377 Dark Spot Eraser Serum | 131000 | product-image-20.png